## product backlog
Product Backlog
Id | User Stories | User Story Id | Priority | Scrum team assigned | status | Estimated story points
1 | User Registration | user 001 | High | Team B | Completed | 8
2 | User Login | user 002 | High | Team A | Completed | 5
3 | Product Search | user 003 | High | Team C | under planning | 5
4 | Product Listings | user 004 | High | Team C | Designing | 8
5 | Product Details | user 005 | Medium | Team C | Designing | 5
6 | Shopping Cart and Checkout | user 006 | High | Team A | In progress | 8
7 | Payment Gateway | user 007 | High | Team A | under planning | 5
8 | Order Tracking | user 008 | Medium | Team B | Designing | 5
9 | Reviews and Ratings | user 009 | Medium | Team B | Designing | 3
10 | Admin Dashboard | user 010 | High | Team C | under planning | 8
11 | Notifications | user 011 | Medium | Team A | In progress | 5
12 | Password Recovery | user 012 | Medium | Team A | under planning | 3
13 | User Dashboard | user 013 | Medium | Team B | Designing | 8
14 | Settings | user 014 | Medium | Team B | Designing | 5

## Sprint backlog
Sprint Duration: 2 weeks
Sprint Goal: Implement key functionalities for user management and e-commerce features.
Sprint Backlog
User Story Id | User Story Name | User Description |  |  | Assigned To | Estimated Time (hours) | Actual Time (hours) | Status | Remarks
|  | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal>
user 001 | User Registration | New user | register | create an account | Team B | 20 | 18 | In Progress | Backend almost complete
user 002 | User Login | User | log in | access my account securely | Team A | 15 | 14 | Completed | Successfully implemented
user 003 | Product Search | User | search for products | find items I want to purchase | Team C | 10 | - | Under Planning | Planning phase started
user 004 | Product Listings | User | view a list of products | see available items for purchase | Team C | 12 | - | Designing | Designing product listing page
user 005 | Product Details | User | view product details | get detailed information about a product | Team C | 10 | - | Designing | Product details design ongoing
user 006 | Shopping Cart and Checkout | User | add items to my cart and checkout | purchase products conveniently | Team A | 20 | - | In Progress | Initial implementation started
user 007 | Payment Gateway | User | make payments | complete my purchase securely | Team A | 15 | - | Under Planning | Planning phase started
user 008 | Order Tracking | User | track my orders | know the status of my purchases | Team B | 12 | - | Designing | Order tracking system design
user 009 | Reviews and Ratings | User | leave reviews and ratings | share my feedback on products | Team B | 8 | - | Designing | Reviews and ratings design
user 010 | Admin Dashboard | Admin | view overall site analytics | manage the platform effectively | Team C | 15 | - | Under Planning | Planning phase started
user 011 | Notifications | User | receive notifications | get updates on specific activities | Team A | 9 | - | In Progress | Initial implementation started
user 012 | Password Recovery | User | recover my password | regain access to my account if forgotten | Team A | 8 | - | Under Planning | Planning phase started
user 013 | User Dashboard | User | view a dashboard | see my activity and statistics | Team B | 14 | - | Designing | User dashboard design ongoing
user 014 | Settings | User | adjust my settings | personalize my experience | Team B | 10 | - | Designing | Settings page design ongoing